## Definitions
Definitions for Quarterly Status Spreadsheet Terms
Term | Definition
CAP | Corrective Action Plan. A series of steps/actions an agency plans to take to correct the issue(s) identified in a finding.
CAP Status | "Complete" means all steps of an agency's CAP are complete and the issue identified in the finding should not recur. "In Process" means not all CAP steps have been completed as yet. "N/A" signifies the agency's disagreement with a finding and that they feel no CAP is necessary.
Finding # | The finding number as designated in the Single Audit report. The first four digits indicate the year, e.g. 2021-XXX.
Questioned Costs | As defined in the Uniform Grant Guidance (UGG), 2 CFR Part 200.84, questioned cost means a cost that is questioned by the auditor because of an audit finding: (a) Which resulted from a violation or possible violation of a statute, regulation, or the terms and conditions of a Federal award, including for funds used to match Federal funds; (b) Where the costs, at the time of the audit, are not supported by adequate documentation; or (c) Where the costs incurred appear unreasonable and do not reflect the actions a prudent person would take in the circumstances.
Resolution Status | "Resolved" means the agency has received a resolution letter (i.e. correspondence indicating that the CAP is considered to be adequate) from the federal agency responsible for resolving the finding. "Unresolved" means the agency has not yet received a resolution letter from the federal agency. "Closed" signifies that a finding has been closed in accordance with UGG, 2 CFR Part 200.511 which states:
(3) ...A valid reason for considering an audit finding as not warranting further action is that all of the following have occurred:
(i) Two years have passed since the audit report in which the finding occurred was submitted to the Federal Audit Clearinghouse (FAC);
(ii) The Federal agency or pass-through entity is not currently following up with the auditee on the audit finding; and
(iii) A management decision was not issued.

## Federal Agency Abbreviations
Federal Agency Abbreviations
Abbreviation | Federal Agency
DHS | United States Department of Homeland Security
DOD | United States Department of Defense
DOE | United States Department of Energy
DOI | United States Department of the Interior
DOJ | United States Department of Justice
DOL | United States Department of Labor
DOT | United States Department of Transportation
DVA | United States Department of Veterans Affairs
EPA | United States Environmental Protection Agency
HHS | United States Department of Health and Human Services
HUD | United States Department of Housing and Urban Development
TREAS | United States Treasury
USDA | United States Department of Agriculture
USDE | United States Department of Education

## DHS
Status of Unresolved Audit Findings - Department of Human Services
[5 empty] | Resolution as of 3-31-2024 |  |  | Resolution as of 12-31-2023 |  |  | Resolution as of 09-30-2023 |  |  | Resolution as of 06-30-2023 |  |  | Resolution as of 03-31-2023 |  |  | Resolution as of 12-31-2022 |  |  | Resolution as of 09-30-2022 |  |  | Resolution as of 06-30-2022
[5 empty] | Status |  |  | Status |  |  | Status |  |  | Status |  |  | Status |  |  | Status |  |  | Status |  |  | Status
Finding # | Finding Title | Resolution Federal Agency | Prior Year Finding | Questioned Costs | CAP | Finding |  | CAP | Finding |  | CAP | Finding |  | CAP | Finding |  | CAP | Finding |  | CAP | Finding |  | CAP | Finding |  | CAP | Finding
2021-006 | A Significant Deficiency and Noncompliance Exist at the Department of Human Services Related to Submission of Emergency Rental Assistance Monthly and Quarterly Reporting | TREAS | N/A | N/A | Complete | Closed | This finding has been closed in accordance with UGG, 2 CFR Part 200.511. | Complete | Unresolved | See Finding 2022-007. | Complete | Unresolved | See Finding 2022-007. | Complete | Unresolved | See Finding 2022-007. | Complete | Unresolved | CAP is considered complete. Awaiting federal resolution. | Complete | Unresolved | CAP is considered complete. Awaiting federal resolution. | Complete | Unresolved | CAP is considered complete. Awaiting federal resolution. | Complete | Unresolved | A contractor was hired to perform the necessary data validation. With the tight timeframes, there isn't time to perform this validation prior to submission to Treasury; however, DHS obtained permission from Treasury to make any necessary corrections to the submissions after the initial submission. Therefore, the contractor is validating the information after the initial submission, and DHS will make any necessary corrections.
2021-007 | Department of Human Services Did Not Validate Financial Information as Part of Its On-Site Monitoring of Temporary Assistance for Needy Families Subrecipients | HHS/ACF | 2020-006 | N/A | Complete | Resolved | Received federsl resolution correspondence. | In Process | Unresolved | See Finding 2022-008. | In Process | Unresolved | See Finding 2022-008. | In Process | Unresolved | See Finding 2022-008. | In Process | Unresolved | Awaiting grantee's response to DHS OGC. | In Process | Unresolved | Awaiting grantee's response to DHS OGC. | In Process | Unresolved | DHS OGC is still in the process of responding to the grantee's attorney. Due to these ongoing issues, monitoring was not completed by June 30, 2022. The next steps are dependent on the grantee's response to DHS OGC. | In Process | Unresolved | OIM-TANF - New Directions, Cash Grants - - Currently, the updates need to be completed and will be implemented when onsite monitoring resumes. Office of Policy Development (OPD)-Alternatives to Abortion (AA) - On February 7, 2022, DHS OGC spoke with the grantee’s attorney regarding the requested documentation for monitoring. On February 14, DHS OGC received an email from the grantee’s attorney outlining Real Alternatives’ position on a potential resolution of the issue regarding DHS access to certain requested documents. Rather than offering a resolution, Real Alternatives has taken a new position regarding DHS access. For the first time, Real Alternative asserts that DHS is not entitled to access certain requested documents at all. Further, it continues to assert that DHS will only be provided access to the other requested documents on-site and will not be allowed to make copies of those documents. Although DHS is agreeable to access documents on-site, it needs to make copies of certain documents so that it can verify the costs of rendered services against its records. DHS OGC is currently working on a response to the grantee’s attorney. Due to these ongoing issues, this finding is likely to be repeated.
2021-009 | A Significant Deficiency and Noncompliance Exist at the Department of Human Services Related to the Medicaid National Correct Coding Initiative | HHS/CMS | 2020-010 | N/A | Complete | Closed | This finding has been closed in accordance with UGG, 2 CFR Part 200.511. | Complete | Unresolved | See Finding 2022-009. | Complete | Unresolved | See Finding 2022-009. | Complete | Unresolved | See Finding 2022-009. | Complete | Unresolved | CAP is considered complete. Awaiting federal resolution. | Complete | Unresolved | CAP is considered complete. Awaiting federal resolution. | Complete | Unresolved | CAP is considered complete. Awaiting federal resolution. | Complete | Unresolved | OMAP’s Bureau of Data and Claims Management (BDCM) executed the amendment to the PROMISe contract with Gainwell Technologies which includes the necessary NCCI Confidentiality Agreement.
2021-014 | State Agencies Did Not Identify the Federal Award Information and Applicable Requirements at the Time of the Subaward and Did Not Evaluate Each Subrecipient’s Risk of Noncompliance as Required by the Uniform Grant Guidance | HHS/ACF | 2020-020 | N/A | Complete | Resolved | Received federal resolution correspondence. | Complete | Unresolved | See Finding 2022-013. | Complete | Unresolved | See Finding 2022-013. | Complete | Unresolved | See Finding 2022-013. | Complete | Unresolved | CAP is considered complete. Awaiting federal resolution. | Complete | Unresolved | CAP is considered complete. Awaiting federal resolution. | Complete | Unresolved | CAP is considered complete. Awaiting federal resolution. | Complete | Unresolved | CAP is considered complete. Awaiting federal resolution.
2021-015 | A Material Weakness and Material Noncompliance Exist in the Commonwealth’s Subrecipient Audit Resolution Process | HHS/ACF, HHS/ARD, HHS/CMS | 2020-021 | N/A | Complete | Closed | This finding has been closed in accordance with UGG, 2 CFR Part 200.511. | Complete | Unresolved | See Finding 2022-014. | Complete | Unresolved | See Finding 2022-014. | Complete | Unresolved | See Finding 2022-014. | Complete | Unresolved | DHS issued letters to those subrecipients who are late with their audits that we will begin withholding five percent of their state funding in July 2023 until their audits are submitted. Related to the timeliness of management decisions, the backlog has been eliminated! Although this finding will be repeated for the year ending June 30, 2023, since the backlog existed during the year, it should not be repeated for the year ending June 30, 2024. | In Process | Unresolved | Related to the timeliness of management decisions, although this finding will be repeated for the year ended June 30, 2022, since the backlog existed during the year, it should not be repeated for the year ending June 30, 2023. | In Process | Unresolved | The backlog is close to being eliminated. Although this finding will be probably be repeated for the year ended June 30, 2022, since the backlog existed during the year, it should not be repeated for the year ending June 30, 2023. | In Process | Unresolved | Related to the late submissions of subrecipient audit reports, ACF did not sustain this part of the finding. ACF resolved the finding for CCDF. Related to the timeliness of management decisions, the backlog is close to being eliminated. Although this finding will probably be repeated for the year ended June 30, 2022, since the backlog existed during the year, it should not be repeated for the year ending June 30, 2023.
2022-006 | A Material Weakness and Material Noncompliance Exist at the Department of Human Services Related to Electronic Benefits Transfer Card Security | HHS-ACF, USDA | 2021-005 | N/A | Complete | Unresolved | The CAP is complete for this finding. Awaiting federal resolution. | Complete | Unresolved | The CAP is complete for this finding. Awaiting USDA resolution. | Complete | Unresolved | The CAP is complete for this finding. Awaiting USDA resolution. | Complete | Unresolved | The CAP is complete for this finding. Awaiting federal resolution.
2022-007 | A Significant Deficiency and Noncompliance Exist at the Department of Human Services Related to Submission of Emergency Rental Assistance Monthly and Quarterly Reporting and Special Tests and Provisions Related to ERA Funds Reallocation | TREAS | 2021-006 | N/A | Complete | Unresolved | The CAP is complete for this finding. Awaiting federal resolution. | Complete | Unresolved | The CAP is complete for this finding. Awaiting federal resolution. | Complete | Unresolved | The CAP is complete for this finding. Awaiting federal resolution. | Complete | Unresolved | The CAP is complete for this finding. Awaiting federal resolution.
2022-008 | Department of Human Services Did Not Validate Financial Information as Part of Its On-Site Monitoring of Temporary Assistance for Needy Families Subrecipients | HHS-ACF | 2021-007 | N/A | In Process | Unresolved | OIM is continuing to research monitoring options. OPD is still awaiting the grantee's response to legal counsel. | In Process | Unresolved | OPD is awaiting the grantee's response to DHS OGC. OIM is researching options to complete effective monitoring. | In Process | Unresolved | OIM-TANF - OIM is currently exploring different monitoring options. Office of Policy Development (OPD)-Alternatives to Abortion (AA) - DHS OGC is still in the process of responding to the grantee's attorney. The next steps are dependent on the grantee's response to DHS OGC. Anticipated completion date is March 2024. | In Process | Unresolved | OIM-TANF - OIM is currently exploring different monitoring options. Office of Policy Development (OPD)-Alternatives to Abortion (AA) - DHS OGC is still in the process of responding to the grantee's attorney. The next steps are dependent on the grantee's response to DHS OGC. Anticipated completion date is March 2024.
2022-009 | A Significant Deficiency and Noncompliance Exist at the Department of Human Services Related to the Medicaid National Correct Coding Initiative | HHS-CMS | 2021-009 | N/A | Complete | Unresolved | Final amendment will be added to the contract by June 30, 2024. | Complete | Unresolved | The CAP is complete for this finding. Awaiting federal resolution. | Complete | Unresolved | The CAP is complete for this finding. Awaiting federal resolution. | Complete | Unresolved | OMAP’s Bureau of Data and Claims Management (BDCM) executed the amendment to the PROMISe contract with Gainwell Technologies which includes the necessary NCCI Confidentiality Agreement.
2022-013 | State Agencies Did Not Identify the Federal Award Information and Applicable Requirements at the Time of the Subaward and Did Not Evaluate Each Subrecipient’s Risk of Noncompliance as Required by the Uniform Grant Guidance | HHS-ACF,ARD | 2021-014 | N/A | Complete | Resolved | Received all federal resolution correspondence. | Complete | Unresolved | The CAP is complete for this finding. Awaiting federal resolution. | Complete | Unresolved | The CAP is complete for this finding. Awaiting federal resolution. | Complete | Unresolved | The CAP is complete for this finding. Awaiting federal resolution.
2022-014 | A Material Weakness and Material Noncompliance Exist in the Commonwealth’s Subrecipient Audit Resolution Process | TREAS, HHS-ACF,ARD,CMS | 2021-015 | N/A | Complete | Unresolved | The CAP is complete for this finding. Awaiting federal resolution. | Complete | Unresolved | The CAP is complete for this finding. Awaiting federal resolution. | Complete | Unresolved | The CAP is complete for this finding. Awaiting federal resolution. | Complete | Unresolved | Letters will now be issued to those subrecipients who are late with their audits informing them that we will begin withholding 5% of their state funding until their audits are submitted. Although this finding may be repeated for the year ending June 30, 2023, since the backlog existed during the year, it is now gone and the finding should not be repeated going forward.

## DOH
Status of Unresolved Audit Findings - Department of Health
[5 empty] | Resolution as of 3-31-2024 |  |  | Resolution as of 12-31-2023 |  |  | Resolution as of 09-30-2023 |  |  | Resolution as of 06-30-2023
[5 empty] | Status |  |  | Status |  |  | Status |  |  | Status
Finding # | Finding Description | Resolution Federal Agency | Prior Year Finding | Questioned Costs | CAP | Finding |  | CAP | Finding |  | CAP | Finding |  | CAP | Finding
2022-013 | State Agencies Did Not Identify the Federal Award Information and Applicable Requirements at the Time of the Subaward and Did Not Evaluate Each Subrecipient’s Risk of Noncompliance as Required by the Uniform Grant Guidance | HHS-CDC | N/A | N/A | In Process | Unresolved | Monitoring division given a new target date to be fully operational March 31, 2025. | In Process | Unresolved | Contractors are in negotiation for the monitoring division. | In Process | Unresolved | No change in Education Portion. Assessment portion completion is delayed due to lack of state funding for the Monitoring division. Contractors and alternatives are being considered for the Monitoring division. | In Process | Unresolved | The following CAP portion is currently awaiting legal and leadership review and approval: Educate Department: Budget Office is developing a bulletin that will outline the subrecipient monitoring requirements with links to State and Federal Sources. The bulletin will be shared with all program office staff. The Budget Office will develop the following templates and provide to all program offices: - Determination of vendor status: Subrecipient or Contractor - Risk Assessment Form - Internal Control Self-Assessment for Subrecipient Template - Subrecipient Monitoring Template
2022-014 | A Material Weakness and Material Noncompliance Exist in the Commonwealth’s Subrecipient Audit Resolution Process | USDA | N/A | N/A | Complete | Unresolved | The CAP is complete for this finding. Awaiting federal resolution. | Complete | Unresolved | The CAP is complete for this finding. Awaiting federal resolution. | Complete | Unresolved | The CAP is complete for this finding. Awaiting federal resolution. | Complete | Unresolved | The CAP is complete for this finding. Awaiting federal resolution.

## OA
Status of Unresolved Audit Findings - Office of Administration
[5 empty] | Resolution as of 3-31-2024 |  |  | Resolution as of 12-31-2023 |  |  | Resolution as of 09-30-2023 |  |  | Resolution as of 06-30-2023
[5 empty] | Status |  |  | Status |  |  | Status |  |  | Status
Finding # | Finding Title | Resolution Federal Agency | Prior Year Finding | Questioned Costs | CAP | Finding |  | CAP | Finding |  | CAP | Finding |  | CAP | Finding
2022-010 | Controls Over Information Technology System Migration and Controls Over the Accountability of Donated Foods Need Improvement | USDA | N/A | N/A | Complete | Resolved | CAP is complete. | In Process | Resolved | The CEDC BA will implement the testing strategy and develop test plan/cases based on strategy for use in User Acceptance Testing (UAT). Estimated completion date April 2024. | In Process | Resolved | Incorporated INF000 into the development framework in August and will be utilized as appropriate. Working on implementing a testing strategy and developing test plan/cases for use in User Acceptance Testing. Received USDA resolution letter. | In Process | Unresolved | Working on incorporating INF000 into development framework and developing a testing strategy. Still expected to be complete by 9/30/23.

## OB
Status of Unresolved Audit Findings - Office of the Budget
[5 empty] | Resolution as of 3-31-2024 |  |  | Resolution as of 12-31-2023 |  |  | Resolution as of 09-30-2023 |  |  | Resolution as of 06-30-2023
[5 empty] | Status |  |  | Status |  |  | Status |  |  | Status
Finding # | Finding Title | Resolution Federal Agency | Prior Year Finding | Questioned Costs | CAP | Finding |  | CAP | Finding |  | CAP | Finding |  | CAP | Finding
2022-011 | A Significant Deficiency and Noncompliance Exist Related to Preparation of the Interim Report | TREAS | N/A | N/A | Complete | Unresolved | Awaiting federal resolution. Finding was not repeated. | Complete | Unresolved | Awaiting federal resolution. | Complete | Unresolved | Awaiting federal resolution. | Complete | Unresolved | Awaiting Federal resolution.

## PDA (hidden)
Status of Unresolved Audit Findings - Department of Agriculture
[5 empty] | Resolution as of 09-30-2023 |  |  | Resolution as of 06-30-2023
[5 empty] | Status |  |  | Status
Finding # | Finding Title | Resolution Federal Agency | Prior Year Finding | Questioned Costs | CAP | Finding |  | CAP | Finding
2022-010 | Controls Over Information Technology System Migration and Controls Over the Accountability of Donated Foods Need Improvement | USDA | N/A | N/A | Complete | Resolved | Item #5 on the CAP is complete. All Commodity Distributor Inventory Reports were reconciled prior to October 1, 2023 and inventory balances at commodity distributors agreed with year-end physical inventory counts. Received USDA resolution letter. | In Process | Unresolved | MPRs are now being completed in a timely manner and routinely being filed in accordance with USDA's prescribed schedule. Upon receipt of monthly data imports from the Commodity Distributors, BFA works with both the Commodity Distributors and USDA to mutually resolve any discrepancies and achieve reconciliation with all USDA receipts. Item #5 on the CAP is still pending completion by September 2023. It is dependent on BFA first completing the annual on-site physical inventory of the Commodity Distributors on the final two days of June.

## PDE
Status of Unresolved Audit Findings - Education
[5 empty] | Resolution as of 3-31-2024 |  |  | Resolution as of 12-31-2023 |  |  | Resolution as of 09-30-2023 |  |  | Resolution as of 06-30-2023 |  |  | Resolution as of 03-31-2023 |  |  | Resolution as of 12-31-2022 |  |  | Resolution as of 09-30-2022 |  |  | Resolution as of 06-30-2022
[5 empty] | Status |  |  | Status |  |  | Status |  |  | Status |  |  | Status |  |  | Status |  |  | Status |  |  | Status
Finding # | Finding Title | Resolution Federal Agency | Prior Year Finding | Questioned Costs | CAP | Finding |  | CAP | Finding |  | CAP | Finding |  | CAP | Finding |  | CAP | Finding |  | CAP | Finding |  | CAP | Finding |  | CAP | Finding
2021-003 | A Significant Deficiency and Noncompliance Exist at the Department of Education Related to Submission of Elementary and Secondary School Emergency Relief Fund Annual Reporting | USDE | N/A | N/A | Complete | Closed | This finding has been closed in accordance with UGG, 2 CFR Part 200.511. | Complete | Unresolved | CAP is complete. PDE is awaiting USDE's PDL. | Complete | Unresolved | CAP is complete. PDE is awaiting USDE's PDL. | Complete | Unresolved | CAP is complete. PDE is awaiting USDE's PDL. | Complete | Unresolved | CAP is complete. PDE is awaiting USDE's PDL. | Complete | Unresolved | CAP is complete. PDE is awaiting USDE's PDL. | Complete | Unresolved | CAP is complete. PDE is awaiting USDE's PDL. | In Process | Unresolved | PDE corrective action has been implemented. Continuous and ongoing data review will occur through PIMS data validation upon entering and through ESSR monitoring. PDE is awaiting USDE's PDL.
2022-004 | A Significant Deficiency and Noncompliance Exist at the Department of Education Related to Submission of GEER, ESSER, and CRRSA EANS Annual Reporting | USDE | 2021-003 | N/A | Complete | Unresolved | CAP is complete. PDE is awaiting USDE's PDL. Finding was not repeated. | Complete | Unresolved | CAP is complete. PDE is awaiting USDE's PDL. | Complete | Unresolved | CAP is complete. PDE is awaiting USDE's PDL. | Complete | Unresolved | The ESSER Monitoring Team works collaboratively with the Data Quality team to collect all ESSER/GEER and other covid funded data in the Pennsylvania Information Management System. We have successfully collected, verified and submitted all required data to USDE by the given deadlines and correction windows. The ESSER Monitoring Team meets regularly with USDE and discusses data and data quality.
2022-014 | A Material Weakness and Material Noncompliance Exist in the Commonwealth’s Subrecipient Audit Resolution Process | USDE, USDA | N/A | N/A | Complete | Unresolved | CAP is complete. PDE is awaiting federal resolution. | Complete | Unresolved | CAP is complete. PDE is awaiting federal resolution. | Complete | Unresolved | CAP is complete. PDE is awaiting federal resolution. | In Process | Unresolved | PDE is finalizing the implementation of corrective action and is awaiting USDE's Program Determination Letter.